Sprint 9 Planning - Part 2

**3/8/2022 - 3/18/2022**

**Capacity Estimates:**

* Individual:
  + Colin: 10 story points
  + Leon: 12 story points
  + Orion: 11 story points
  + An: 10 story points
  + Andy: 9 story points
* **Total: 52 story points**

**Updated Story Point Estimates:**

* Individual
  + Authorization - Finish: 8
  + Authentication - Finish: 11
  + Account Creation - Finish: 9
  + Account Deletion - Finish: 9
  + Logout - Finish: 8
* **Total**: **45 story points**

**Authorization – Finish**

* **Original Story Point Estimate:** 9
* **Assigned to:** Colin
* **Task Breakdown:** 
  + Finish Check Authorization Method
    - Individual story point estimate: 3
  + Update LLD Sequence Diagrams
    - Individual story point estimate: 2
  + Testing
    - Individual story point estimate: 3
  + **Updated Story Point Estimate: 8**

**Authentication – Finish**

* **Original Story Point Estimate:** 10
* **Assigned to:** Leon Chen
* **Task Breakdown:** 
  + Finish One Time Password
    - Individual story point estimate: 3
  + Finish username and password check
    - Individual story point estimate: 3
  + Finish logic for disabling and enabling account after success/fails
    - Individual story point estimate: 2
  + Finish Testing
    - Individual story point estimate: 3
  + **Updated Story Point Estimate: 11**

**Account Creation – Finish**

* Original Story Point Estimate: 8
* **Assigned to:** Andy
* **Task Breakdown:** 
  + Finish account creation view
    - Individual story point estimate: 2
  + Finish Email validation
    - Individual story point estimate: 1
  + Password validation:
    - Individual story point estimate: 1
  + Update LLD Sequence Diagrams
    - Individual story point estimate: 3
  + Finish Testing
    - Individual story point estimate: 2
  + **Updated Story Point Estimate: 9**

**Account Deletion – Finish**

* Original Story Point Estimate: 7
* **Assigned to:** Orion
* **Task Breakdown:** 
  + Finish security requirements
    - Individual story point estimate: 3
  + Finish proper user claims allocation
    - Individual story point estimate: 3
  + Finish Testing
    - Individual story point estimate: 3
* **Updated Story Point Estimate: 9**

**Logout – Finish**

* Original Story Point Estimate: 7
* **Assigned to:** An
  + Dedicated story points: 10
* **Task Breakdown:** 
  + Finish integration with authentication status
    - Individual story point estimate: 2
  + Finish session termination function
    - Individual story point estimate: 2
  + Update LLD sequenced diagrams
    - Individual story point estimate: 2
  + Finish Testing
    - Individual story point estimate: 2
* **Updated Story Point Estimate: 8**