## Kanban
Project Backlog
Type | Who | Feature or Activity | Estimated Hours | Priority Points | Internal Due Date | External Due Date | Sprint | Details
😴 | Backlog
Feature | Orion | Usage Analysis Dashboard | 20 | 7 | 2022-02-21 | 2022-05-08 | 8
Feature | Colin | Authorization | 19 | 8 | 2022-02-21 | 2022-05-08 | 7
Feature | Andy | Account Registration | 25 | 8 | 2022-02-21 | 2022-05-08 | 7
Feature | Leon | Make appropriate tables | 2 | 6 | 2022-02-21 | 2022-05-08 | 7
Feature | Leon | Add logic for disabling and enabling account after success/fails | 2 | 6 | 2022-02-21 | 2022-05-08 | 7
Feature | Leon | Valid username and password check | 3 | 8 | 2022-02-21 | 2022-05-08 | 7
Feature | Leon | Include token in authorization header in client | 1 | 8 | 2022-02-21 | 2022-05-08 | 7
Feature | Leon | One Time Password | 3 | 6 | 2022-02-21 | 2022-05-08 | 7
Feature | Leon | Create and pass token to client | 2 | 5 | 2022-02-21 | 2022-05-08 | 7
Feature | An | Data Collection |  | 5 | 2022-02-21 | 2022-05-08 | 9
Feature | Colin | Hazard Restrictions |  | 4 | 2022-02-21 | 2022-05-08 | 9
Feature | Colin | Route Waypoints |  | 7 | 2022-02-21 | 2022-05-08 | 9
Feature | Orion | History Tracker | 15 | 4 | 2022-02-21 | 2022-05-08 | 9
Update | Andy | ML-Based Algo improvement |  | 7 | 2022-02-21 | 2022-05-08 | 9
Feature | Leon | Registration | 25 | 10 | 2022-02-21 | 2022-05-08 | 8
Feature | Andy | User Analysis Dashboard |  | 7 | 2022-03-07 | 2022-05-08 | 8
Feature | An | Login/Logout | 9 | 10 | 2022-03-07 | 2022-05-08 | 7
Feature | Orion | User Access Control | 15 | 6 | 2022-03-07 | 2022-05-08 | 8
Task | Colin | Error Handling |  | 9 | 2022-03-07 | 2022-05-08 | 8
Feature | Leon | Network Communication |  | 10 | 2022-03-07 | 2022-05-08 | 8
Documentation | An | Documentation | 15 | 5 | 2022-03-07 | 2022-05-08 | 8
Feature | Orion | Hazard labels | 20 | 5 | 2022-03-07 | 2022-05-08 | 9
Feature | All | UI |  | 8 | 2022-03-07 | 2022-05-08 | 9
😃 | In Progress
Task | Andy | Setup account creation view | 3 | 8 | 2022-05-08 | 2021-12-15 | 7
Task | Andy | Email validation | 4 | 8 | 2022-05-08 | 2021-12-15 | 7
Task | Andy | password validation | 4 | 7 | 2022-05-08 | 2021-12-15 | 7
Task | Andy | setup email verification service | 5 | 7 | 2022-05-08 | 2021-12-15 | 7
Task | Andy | draft LLD sequence diagrams | 4 | 8 | 2022-05-08 | 2021-12-15 | 7
Task | Andy | account creation testing | 3 | 6 | 2022-05-08 | 2021-12-15 | 7
😎 | Done
Documentation | Orion | Logging UML | 8 | 17 | 2021-12-05 | 2021-12-15 | 4 | Milestone 3
Feature | Andy | Logging Code | 5 | 9 | 2021-12-05 | 2021-12-15 | 3 | Milestone 3
Documentation | Leon | User Management UML | 3 | 14 | 2021-12-05 | 2021-12-15 | 4 | Milestone 3
Feature | Leon | User Management Code | 5 | 8 | 2021-12-05 | 2021-12-15 | 6 | Milestone 3
Feature | Orion | Security Code | 5 | 10 | 2021-12-05 | 2021-12-15 | 6 | Milestone 3
Documentation | Orion | BRD revision | 4 | 20 | 2021-12-05 | 2021-12-15 | 4 | Milestone 3
Feature | An | Archiving code | 4 | 7 | 2021-12-05 | 2021-12-15 | 6 | Milestone 3
Feature | Orion | Database setup | 2 | 19 | 2021-12-05 | 2021-12-15 | 6 | Milestone 3
Documentation | Leon | Tech Approval for frontend | 8 | 24 | 2021-12-05 | 2021-12-15 | 4
Documentation | Andy | Tech Approval for testing suite | 2 | 21 | 2021-12-05 | 2021-12-15 | 6 | Milestone 3
Documentation | An | User Management CRC | 3 | 12 | 2021-12-05 | 2021-12-15 | 5 | Milestone 3
Documentation | An | Archiving LLD | 4 | 11 | 2021-12-05 | 2021-12-15 | 6 | Milestone 3
Documentation | An | Security LLD | 2 | 18 | 2021-12-05 | 2021-12-15 | 6 | Milestone 3
Documentation | Team | Business Requirements Document |  | 6 | 2021-10-03 | 2021-10-08 | 2021-01-02 | Milestone 1
Documentation | Team | Tech Spec |  | 1 | 2021-10-03 | 2021-10-08 | 2021-01-02 | Milestone 1
Documentation | Team | High-level design document |  | 2 | 2021-10-03 | 2021-10-08 | 2021-01-02 | Milestone 1
Documentation | Team | Project Plan |  | 5 | 2021-10-30 | 2021-11-03 | 3 | Milestone 2
Documentation | Team | Network Diagram |  | 3 | 2021-10-30 | 2021-11-03 | 3 | Milestone 2
Documentation | Team | Test Plan |  | 4 | 2021-10-30 | 2021-11-03 | 3 | Milestone 2
Documentation | Andy | Logging CRC | 2 | 15 | 2021-10-30 | 2021-12-15 | 5 | SCRAPPED - worked on but ultimately decided not to include
Documentation | Andy | Logging Sequence diagram | 4 | 16 | 2021-10-30 | 2021-12-15 | 5 | SCRAPPED - worked on but ultimately decided not to include
Documentation | An | User Management Sequence | 5 | 13 | 2021-10-30 | 2021-12-15 | 5 | SCRAPPED - worked on but ultimately decided not to include
Feature | Andy | Tech Approval for HTML | 4 | 23 | 2021-10-30 | 2021-12-15 | 4 | Worked on, ultimately moved to next semester
Documentation | Andy | Tech Approval for CSS | 4 | 22 | 2021-10-30 | 2021-12-15 | 4 | Worked on, ultimately moved to next semester
Task | Orion | Setup login page |  |  | 2022-02-21 | 2022-05-08 | 7
Task | Orion | Configure ports |  |  | 2022-02-22 | 2022-05-09 | 7
Task | Orion | Setup CORS |  |  | 2022-02-23 | 2022-05-10 | 7
Task | Orion | Setup frontend routing |  |  | 2022-02-24 | 2022-05-11 | 7
Task | Orion | Setup VS startup configuration |  |  | 2022-02-25 | 2022-05-12 | 7
Task | Orion | Integrate frontend project files |  |  | 2022-02-26 | 2022-05-13 | 7
TYPE LEGEND |  | PRIORITY POINTS:
Feature |  | Priority points are a quantitative representation of the value each item brings to the team.
Content
Update
Task
Documentation

## Help
HELP | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/agile-kanban-board.html
Copyright & Terms of Use (Limited Private Sharing)
This spreadsheet, including all worksheets and associated content is copyrighted. Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
About This Template
This worksheet was designed as an online collaborative Kanban board for use in Agile Project Management where the team members may be working remotely. Instead of columns for Backlog, To Do, In Progress, Testing, and Done, the spreadsheet uses horizontal lanes. Rows within the worksheet represent cards or sticky notes. Create new "cards" by inserting rows. Move cards between lanes by dragging and dropping the entire row.
Create New Cards / Tasks
Just insert a new row below or above an existing card or task. Note: In Google Sheets, when you insert a row above or below the selected line, the formatting in the newly inserted row is based on the row you have selected.
Move Cards to new Lanes
Select the row, then drag and drop the row by dragging the row number (the row number on the far left of the spreadsheet).
Show/Hide rows
You'll probably want to show/hide the rows in the Backlog. You can do that by just selecting the rows, right-clicking on the row numbers, and selecting Hide Rows. Google Sheets will display up/down arrows when rows are hidden, so to show them, click on the arrows.
After Each Sprint
1) Update the RecordBook worksheet with the results of the sprint.
2) Create a copy of this spreadsheet and rename the copy based on the date of the sprint (e.g. "Sprint - 2017 11 27") and store the copy in an archived folder. You could duplicate the Kanban worksheet instead and rename the duplicate to store previous sprints within the same workbook.
3) Begin a new sprint by removing the tasks in the Done section and adding, moving and reprioritizing the tasks that you will focus on for the next sprint.
IMPORTANT note about File Sharing via Google Sheets
When sharing the spreadsheet with somebody else, share it with a specific email address only (i.e. an email associated with a Google Account). Using the "Public on the web" or "Anyone with the link" option can comprise the security of your information and will also be a violation of the terms of use for this template.
Do not use the "Public on the Web" option
Do not use the "Anyone with the link" option
Like this Template?
Share the following link to vertex42.com via email, facebook, linkedin, etc. You may share this spreadsheet among your team members and management, but to recommend the template to people outside your company, please only share the link to vertex42.com, not the actual spreadsheet. Thank you!
https://www.vertex42.com/ExcelTemplates/agile-kanban-board.html