## Colin Burndown
Sprint 7 - Colin
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-20 | 4 | Hazard | N/A | N/A | N/A | 18 | 18 | 18 | Sprint start
2022-04-21 | 2 | Hazard | 60% | 1.2 | #VALUE! | 16.8 | 1.0588 | 16.9412
2022-04-22 | 3 | Hazard | 80% | 2.4 | #VALUE! | 14.4 | 1.0588 | 15.8824
2022-04-23 | 0 | N/A | 0 | 0 | N/A | 14.4 | 1.0588 | 14.8235
2022-04-24 | 4 | Hazard | 90% | 3.6 | #VALUE! | 10.8 | 1.0588 | 13.7647
2022-04-25 | 10 | Hazard | 90% | 9 | N/A | 1.8 | 1.0588 | 12.7059
2022-04-26 | 12 | Hazard | 90% | 10.8 | N/A | -9 | 1.0588 | 11.6471
Sprint End
Total: | 31 |  |  | 27

## Andy Burndown
Sprint 11 - Andy
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-20 | 18 | N/A | N/A | N/A | N/A | 24 | 24 | 24 | Sprint start
2022-04-21 | 3 | Map Direction | 20% | 0.6 | N/A | 23.4 | 1.4118 | 22.5882
2022-04-22 | 6 | Map Direction | 25% | 1.5 | #VALUE! | 21.9 | 1.4118 | 21.1765
2022-04-23 | 0 | N/A | 0% | 0 | N/A | 21.9 | 1.4118 | 19.7647
2022-04-24 | 3 | Map Direction | 25% | 0.75 | N/A | 21.15 | 1.4118 | 18.3529
2022-04-25 | 10 | Map Direction | 25% | 2.5 | N/A | 18.65 | 1.4118 | 16.9412
2022-04-26 | 7 | Map Direction | 60% | 4.2 | N/A | 14.45 | 1.4118 | 15.5294
Sprint End
Total: | 29 |  |  | 9.55

## Leon Burndown
Sprint 11 - Leon
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-20 | 0 | N/A | N/A | N/A | N/A | 18 | 18 | 18 | Sprint start
2022-04-21 | 3 | Overlay | 90% | 2.7 | #N/A | 15.3 | 1.0588 | 16.9412
2022-04-22 | 3 | Overlay | 90% | 2.7 | N/A | 12.6 | 1.0588 | 15.8824
2022-04-23 | 3 | Overlay | 85% | 2.55 | N/A | 10.05 | 1.0588 | 14.8235
2022-04-24 | 6 | Overlay | 75% | 4.5 | #VALUE! | 5.55 | 1.0588 | 13.7647
2022-04-25 | 2 | Overlay | 90% | 1.8 | N/A | 3.75 | 1.0588 | 12.7059
2022-04-26 | 2 | Overlay | 90% | 1.8 | #VALUE! | 1.95 | 1.0588 | 11.6471
Sprint End
Total: | 19 |  |  | 16.05

## Orion Burndown
Sprint 11 - Orion
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-20 | 4 | REPORT HAZARDS | 90% | 90% | N/A | 20 | 20 | 20 | Sprint start
2022-04-21 | 2 | REPORT HAZARDS | 80% | 1.6 | N/A | 18.4 | 1.1765 | 18.8235
2022-04-22 | 4 | REPORT HAZARDS | 75% | 3 | #VALUE! | 15.4 | 1.1765 | 17.6471
2022-04-23 | 3 | REPORT HAZARDS | 80% | 2.4 | #VALUE! | 13 | 1.1765 | 16.4706
2022-04-24 | 5 | REPORT HAZARDS | 75% | 3.75 | N/A | 9.25 | 1.1765 | 15.2941
2022-04-25 | 2 | REPORT HAZARDS | 80% | 1.6 | #VALUE! | 7.65 | 1.1765 | 14.1176
2022-04-26 | 4 | REPORT HAZARDS | 80% | 3.2 | #VALUE! | 4.45 | 1.1765 | 12.9412
Sprint End
Total: | 20 |  |  | 16.45

## An Burndown
Sprint 11 - An
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-20 | 2 | View Route History | N/A | N/A | N/A | 12 | 12 | 12 | Sprint start
2022-04-21 | 3 | View Route History | 80% | 2.4 | N/A | 9.6 | 0.70588 | 11.2941
2022-04-22 | 5 | View Route History | 80% | 4 | #VALUE! | 5.6 | 0.70588 | 10.5882
2022-04-23 | 0 | N/A | 0% | 0 | N/A | 5.6 | 0.70588 | 9.8824
2022-04-24 | 0 | N/A | 0% | 0 | N/A | 5.6 | 0.70588 | 9.1765
2022-04-25 | 4 | View Route History | 50% | 2 | #VALUE! | 3.6 | 0.70588 | 8.4706
2022-04-26 | 0 | N/A | 0% | 0 | N/A | 3.6 | 0.70588 | 7.7647
Sprint End
Total: | 12 |  |  | 8.4

## Team Burndown
Sprint 7 - Team
Date | Hours Worked | Total Story Points Completed (Actual) | Total Story Points Remaining in Work Items (Actual) | Total Story Points Remaining in Capacity (Actual) | Total Story Points Completed (Ideal) | Total Story Points Remaining (Ideal )
2022-04-20 | 0 | 0 | 106 | 94 | 94 | 94 | Sprint start
2022-04-21 | 13 | 6.1 | 99.9 | 87.9 | 5.5294 | 88.4706
2022-04-22 | 21 | 11.6 | 88.3 | 76.3 | 5.5294 | 82.9412
2022-04-23 | 6 | 4.95 | 83.35 | 71.35 | 5.5294 | 77.4118
2022-04-24 | 18 | 12.6 | 70.75 | 58.75 | 5.5294 | 71.8824
2022-04-25 | 28 | 14.9 | 55.85 | 43.85 | 5.5294 | 66.3529
2022-04-26 | 25 | 20 | 35.85 | 23.85 | 5.5294 | 60.8235
Sprint End
Total: | 111 | 70.15

## Sprint Analysis
Sprint | Team Member | Work Item | Estimated Capacity | Velocity (Actual Capacity) | % Error
3 | Colin | Test Plan | 28 | 46 | 64.29%
| An | Network Diagram | 12 | 10 | -16.67%
| Andy | Test Plan | 8 | 9 | 12.5%
| Orion | Test Plan | 13 | 15 | 15.38%
| Leon | Project Plan | 11 | 9 | -18.18%
| Total | N/A | 72 | 89 | 23.61%
4 | Colin | Logging | 15 | 23 | 53.33%
| An | React DAR | 6 | 8 | 33.33%
| Andy | CSS DAR | 11 | 14 | 27.27%
| Orion | Update BRD | 7 | 6 | -14.29%
| Leon | Vue DAR | 8 | 10 | 25%
| Total | N/A | 47 | 61 | 29.79%
5 | Colin | Logging | 40 | 62 | 55%
| An | UM Sequence Diagrams | 14 | 12 | -14.29%
| Andy | Logging CRC Cards | 17 | 16 | -5.882%
| Orion | Logging LLD | 22 | 25 | 13.64%
| Leon | UM LLD | 18 | 16 | -11.11%
| Total | N/A | 111 | 131 | 18.02%
6 | Colin | **N/A** | **N/A** | **N/A** | 52.99%
| An | Security LLD | 6 | 10 | 66.67%
| Andy | Test Suite DAR | 7 | 12 | 71.43%
| Orion | DB Setup | 11 | 15 | 36.36%
| Leon | UM Source Code | 8 | 11 | 37.5%
| Total | N/A | 32 | 48 | 50%
7 | Colin | New Feature/Authorization | 18 | 27 | 50%
| An | Logout | 16 | 8.4 | -47.5%
| Andy | Account Creation | 24 | 9.55 | -60.21%
| Orion | Initial App Setup | 20 | 16.45 | -17.75%
| Leon | Authentication | 18 | 16.05 | -10.83%
| Total | N/A | 96 | 77.45 | -19.32%
222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222222

## Work Items
Work Item | Initial Story Point Estimate | Updated Story Point Estimate | Assigned to
Authorization | 8 | 19 | Colin
Authentication | 10 | 16 | Leon
Account Creation | 14 | 25 | Andy
Initial App Setup | 8 | 27 | Orion
New Feature | 5 | 7 | Colin
Logout | 5 | 12 | An
Total | 50 | 106