## Colin Burndown
Sprint 7 - Colin
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 18 | 18 | 18 | Sprint start
2022-02-04 | 2 | New Feature | 60% | 1.2 | 5.8 | 16.8 | 1.0588 | 16.9412
2022-02-05 | 3 | New Feature | 80% | 2.4 | 3.4 | 14.4 | 1.0588 | 15.8824
2022-02-06 | 0 | N/A | 0 | 0 | N/A | 14.4 | 1.0588 | 14.8235
2022-02-07 | 2 | New Feature | 75% | 1.5 | 1.9 | 12.9 | 1.0588 | 13.7647
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 12.9 | 1.0588 | 12.7059
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 12.9 | 1.0588 | 11.6471
2022-02-10 | 1 | Authorization | 60% | 0.6 | 18.4 | 12.3 | 1.0588 | 10.5882
2022-02-11 | 2 | Authorization | 70% | 1.4 | 17 | 10.9 | 1.0588 | 9.5294
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 10.9 | 1.0588 | 8.4706
2022-02-13 | 2 | Authorization | 50% | 1 | 16 | 9.9 | 1.0588 | 7.4118
2022-02-14 | 4 | Authorization | 60% | 2.4 | 13.6 | 7.5 | 1.0588 | 6.3529
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 7.5 | 1.0588 | 5.2941
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 7.5 | 1.0588 | 4.2353
2022-02-17 | 4 | Authorization | 60% | 2.4 | 11.2 | 5.1 | 1.0588 | 3.1765
2022-02-18 | 3 | Authorization | 80% | 2.4 | 8.8 | 2.7 | 1.0588 | 2.1176
2022-02-19 | 4 | Authorization | 40% | 1.6 | 7.2 | 1.1 | 1.0588 | 1.0588
2022-02-20 | 5 | Authorization | 75% | 3.75 | 3.45 | -2.65 | 1.0588 | 3.1086e-15 | Sprint End
Total: | 32 |  |  | 20.65
Sprint 8 - Colin
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-22 | 0 | N/A | N/A | N/A | #N/A | 20 | 20 | 20 | Sprint start
2022-02-23 | 1 | Authentication | 70% | 0.7 | 19.3 | 19.3 | 1.6667 | 18.3333
2022-02-24 | 3 | Authentication | 80% | 2.4 | 16.9 | 16.9 | 1.6667 | 16.6667
2022-02-25 | 0 | N/A | 0% | 0 | #N/A | 16.9 | 1.6667 | 15
2022-02-26 | 0 | N/A | 0% | 0 | #N/A | 16.9 | 1.6667 | 13.3333
2022-02-27 | 4 | Authentication | 60% | 2.4 | 14.5 | 14.5 | 1.6667 | 11.6667
2022-02-28 | 3 | Logout | 75% | 2.25 | 11.75 | 12.25 | 1.6667 | 10
2022-03-01 | 0 | N/A | 0% | 0 | #N/A | 12.25 | 1.6667 | 8.3333
2022-03-02 | 6 | Authentication | 80% | 4.8 | 9.7 | 7.45 | 1.6667 | 6.6667
2022-03-03 | 0 | N/A | 0% | 0 | #N/A | 7.45 | 1.6667 | 5
2022-03-04 | 4 | Authentication | 80% | 3.2 | 6.5 | 4.25 | 1.6667 | 3.3333
2022-03-05 | 4 | Authentication | 75% | 3 | 3.5 | 1.25 | 1.6667 | 1.6667
2022-03-06 | 7 | Authentication | 80% | 5.6 | -2.1 | -4.35 | 1.6667 | 0 | Sprint End
Total: | 32 |  |  | 24.35
Sprint 9 - Colin
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-08 | 0 | N/A | N/A | N/A | #N/A | 10 | 10 | 10 | Sprint start
2022-03-09 | 2 | Authentication - Finish | 60% | 1.2 | 9.8 | 8.8 | 1 | 9
2022-03-10 | 0 | N/A | 0% | 0 | #N/A | 8.8 | 1 | 8
2022-03-11 | 3 | Authentication - Finish | 80% | 2.4 | 7.4 | 6.4 | 1 | 7
2022-03-12 | 3 | Authentication - Finish | 75% | 2.25 | 5.15 | 4.15 | 1 | 6
2022-03-13 | 0 | N/A | 0% | 0 | #N/A | 4.15 | 1 | 5
2022-03-14 | 0 | N/A | 0% | 0 | #N/A | 4.15 | 1 | 4
2022-03-15 | 3 | Authentication - Finish | 80% | 2.4 | 2.75 | 1.75 | 1 | 3
2022-03-16 | 0 | N/A | 80% | 0 | #N/A | 1.75 | 1 | 2
2022-03-17 | 3 | Authentication - Finish | 70% | 2.1 | 0.65 | -0.35 | 1 | 1
2022-03-18 | 2 | Authentication - Finish | 80% | 1.6 | -0.95 | -1.95 | 1 | 0 | Sprint End
Total: | 16 |  |  | 11.95
Sprint 10 - Colin
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-28 | 0 | N/A | N/A | N/A | #N/A | 24 | 24 | 24 | Sprint start
2022-03-29 | 2 | Feature - Hazard Restrictions | 70% | 1.4 | 17.6 | 22.6 | 1.1429 | 22.8571
2022-03-30 | 0 | N/A | 0% | 0 | #N/A | 22.6 | 1.1429 | 21.7143
2022-03-31 | 2 | Feature - Hazard Restrictions | 75% | 1.5 | 16.1 | 21.1 | 1.1429 | 20.5714
2022-04-01 | 2 | Feature - Hazard Restrictions | 80% | 1.6 | 14.5 | 19.5 | 1.1429 | 19.4286
2022-04-02 | 0 | N/A | 0% | 0 | #N/A | 19.5 | 1.1429 | 18.2857
2022-04-03 | 2 | Feature - Hazard Restrictions | 90% | 1.8 | 12.7 | 17.7 | 1.1429 | 17.1429
2022-04-04 | 2 | Feature - Hazard Restrictions | 60% | 1.2 | 11.5 | 16.5 | 1.1429 | 16
2022-04-05 | 0 | N/A | 0% | 0 | #N/A | 16.5 | 1.1429 | 14.8571
2022-04-06 | 0 | N/A | 70% | 0 | #N/A | 16.5 | 1.1429 | 13.7143
2022-04-07 | 2 | Feature - Hazard Restrictions | 75% | 1.5 | 10 | 15 | 1.1429 | 12.5714
2022-04-08 | 1 | Feature - Hazard Restrictions | 80% | 0.8 | 9.2 | 14.2 | 1.1429 | 11.4286
2022-04-09 | 2 | Feature - Hazard Restrictions | 80% | 1.6 | 7.6 | 12.6 | 1.1429 | 10.2857
2022-04-10 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 9.1429
2022-04-11 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 8
2022-04-12 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 6.8571
2022-04-13 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 5.7143
2022-04-14 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 4.5714
2022-04-15 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 3.4286
2022-04-16 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 2.2857
2022-04-17 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 1.1429
2022-04-18 | 0 | N/A | 0% | 0 | #N/A | 12.6 | 1.1429 | 8.8818e-15 | Sprint End
Total: | 15 |  |  | 11.4

## Andy Burndown
Sprint 7 - Andy
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 24 | 24 | 24 | Sprint start
2022-02-04 | 0 | N/A | 0% | 0 | N/A | 24 | 1.4118 | 22.5882
2022-02-05 | 4 | Account Creation | 25% | 1 | 24 | 23 | 1.4118 | 21.1765
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 19.7647
2022-02-07 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 18.3529
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 16.9412
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 15.5294
2022-02-10 | 2 | Account Creation | 60% | 1.2 | 22.8 | 21.8 | 1.4118 | 14.1176
2022-02-11 | 0 | N/A | 0% | 0 | N/A | 21.8 | 1.4118 | 12.7059
2022-02-12 | 2 | Account Creation | 50% | 1 | 21.8 | 20.8 | 1.4118 | 11.2941
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 9.8824
2022-02-14 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 8.4706
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 7.0588
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 5.6471
2022-02-17 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 4.2353
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 2.8235
2022-02-19 | 4 | Account Creation | 70% | 2.8 | 19 | 18 | 1.4118 | 1.4118
2022-02-20 | 0 | N/A | 0% | 0 | N/A | 18 | 1.4118 | 3.9968e-15 | Sprint End
Total: | 12 |  |  | 6
Sprint 8 - Andy
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-22 | 0 | N/A | N/A | N/A | #N/A | 18 | 18 | 18 | Sprint start
2022-02-23 | 3 | Account Creation | 70% | 2.1 | 17.9 | 15.9 | 1.5 | 16.5
2022-02-24 | 4 | Account Creation | 50% | 2 | 15.9 | 13.9 | 1.5 | 15
2022-02-25 | 0 | N/A | 0% | 0 | #N/A | 13.9 | 1.5 | 13.5
2022-02-26 | 3 | Account Creation | 80% | 2.4 | 13.5 | 11.5 | 1.5 | 12
2022-02-27 | 0 | N/A | 0% | 0 | #N/A | 11.5 | 1.5 | 10.5
2022-02-28 | 5 | Account Creation | 75% | 3.75 | 9.75 | 7.75 | 1.5 | 9
2022-03-01 | 2 | Account Creation | 60% | 1.2 | 8.55 | 6.55 | 1.5 | 7.5
2022-03-02 | 0 | N/A | 0% | 0 | #N/A | 6.55 | 1.5 | 6
2022-03-03 | 5 | Account Deletion | 90% | 4.5 | 11.5 | 2.05 | 1.5 | 4.5
2022-03-04 | 4 | Account Deletion | 80% | 3.2 | 8.3 | -1.15 | 1.5 | 3
2022-03-05 | 5 | Account Creation | 75% | 3.75 | 4.8 | -4.9 | 1.5 | 1.5
2022-03-06 | 6 | Account Deletion | 80% | 4.8 | 3.5 | -9.7 | 1.5 | 0 | Sprint End
Total: | 37 |  |  | 27.7
Sprint 9 - Andy
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-08 | 0 | N/A | N/A | N/A | #N/A | 9 | 9 | 9 | Sprint start
2022-03-09 | 1 | Authorization - Finish | 60% | 0.6 | 7.4 | 8.4 | 0.9 | 8.1
2022-03-10 | 0 | N/A | 0% | 0 | #N/A | 8.4 | 0.9 | 7.2
2022-03-11 | 0 | N/A | 0% | 0 | #N/A | 8.4 | 0.9 | 6.3
2022-03-12 | 3 | Authorization - Finish | 75% | 2.25 | 5.15 | 6.15 | 0.9 | 5.4
2022-03-13 | 2 | Authorization - Finish | 80% | 1.6 | 3.55 | 4.55 | 0.9 | 4.5
2022-03-14 | 0 | N/A | 0% | 0 | #N/A | 4.55 | 0.9 | 3.6
2022-03-15 | 0 | N/A | 0% | 0 | #N/A | 4.55 | 0.9 | 2.7
2022-03-16 | 3 | Authorization - Finish | 60% | 1.8 | 1.75 | 2.75 | 0.9 | 1.8
2022-03-17 | 3 | N/A | 0% | 0 | #N/A | 2.75 | 0.9 | 0.9
2022-03-18 | 2 | Authorization - Finish | 80% | 1.6 | 0.15 | 1.15 | 0.9 | -1.5543e-15 | Sprint End
Total: | 14 |  |  | 7.85
Sprint 10 - Andy
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-28 | 0 | N/A | N/A | N/A | #N/A | 20 | 20 | 20 | Sprint start
2022-03-29 | 0 | N/A | 0% | 0 | #N/A | 20 | 0.95238 | 19.0476
2022-03-30 | 3 | Feature - Map Directions | 70% | 2.1 | 18.9 | 17.9 | 0.95238 | 18.0952
2022-03-31 | 0 | N/A | 0% | 0 | #N/A | 17.9 | 0.95238 | 17.1429
2022-04-01 | 2 | Feature - Map Directions | 80% | 1.6 | 17.3 | 16.3 | 0.95238 | 16.1905
2022-04-02 | 0 | N/A | 0% | 0 | #N/A | 16.3 | 0.95238 | 15.2381
2022-04-03 | 2 | Feature - Map Directions | 90% | 1.8 | 15.5 | 14.5 | 0.95238 | 14.2857
2022-04-04 | 2 | Feature - Map Directions | 60% | 1.2 | 14.3 | 13.3 | 0.95238 | 13.3333
2022-04-05 | 3 | Feature - Map Directions | 80% | 2.4 | 11.9 | 10.9 | 0.95238 | 12.381
2022-04-06 | 0 | N/A | 0% | 0 | #N/A | 10.9 | 0.95238 | 11.4286
2022-04-07 | 0 | N/A | 0% | 0 | #N/A | 10.9 | 0.95238 | 10.4762
2022-04-08 | 1 | Feature - Map Directions | 80% | 0.8 | 11.1 | 10.1 | 0.95238 | 9.5238
2022-04-09 | 2 | Feature - Map Directions | 75% | 1.5 | 9.6 | 8.6 | 0.95238 | 8.5714
2022-04-10 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | 7.619
2022-04-11 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | 6.6667
2022-04-12 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | 5.7143
2022-04-13 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | 4.7619
2022-04-14 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | 3.8095
2022-04-15 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | 2.8571
2022-04-16 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | 1.9048
2022-04-17 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | 0.95238
2022-04-18 | 0 | N/A | 0% | 0 | #N/A | 8.6 | 0.95238 | -2.8866e-15 | Sprint End
Total: | 15 |  |  | 11.4

## Orion Burndown
Sprint 7 - Orion
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 20 | 20 | 20 | Sprint start
2022-02-04 | 0 | N/A | 0 | 0 | N/A | 20 | 1.1765 | 18.8235
2022-02-05 | 2 | Initial App Setup | 75% | 1.5 | 25.5 | 18.5 | 1.1765 | 17.6471
2022-02-06 | 3 | Initial App Setup | 60% | 1.8 | 23.7 | 16.7 | 1.1765 | 16.4706
2022-02-07 | 0 | N/A | 75% | 0 | N/A | 16.7 | 1.1765 | 15.2941
2022-02-08 | 2 | Initial App Setup | 80% | 1.6 | 22.1 | 15.1 | 1.1765 | 14.1176
2022-02-09 | 2 | Initial App Setup | 80% | 1.6 | 20.5 | 13.5 | 1.1765 | 12.9412
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 13.5 | 1.1765 | 11.7647
2022-02-11 | 3 | Initial App Setup | 70% | 2.1 | 18.4 | 11.4 | 1.1765 | 10.5882
2022-02-12 | 1 | Initial App Setup | 90% | 0.9 | 17.5 | 10.5 | 1.1765 | 9.4118
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 10.5 | 1.1765 | 8.2353
2022-02-14 | 3 | Initial App Setup | 60% | 1.8 | 15.7 | 8.7 | 1.1765 | 7.0588
2022-02-15 | 2 | Initial App Setup | 90% | 1.8 | 13.9 | 6.9 | 1.1765 | 5.8824
2022-02-16 | 3 | Initial App Setup | 85% | 2.55 | 11.35 | 4.35 | 1.1765 | 4.7059
2022-02-17 | 2 | Initial App Setup | 60% | 1.2 | 10.15 | 3.15 | 1.1765 | 3.5294
2022-02-18 | 0 | N/A | 0 | 0 | N/A | 3.15 | 1.1765 | 2.3529
2022-02-19 | 4 | Initial App Setup | 75% | 3 | 7.15 | 0.15 | 1.1765 | 1.1765
2022-02-20 | 1 | Initial App Setup | 80% | 0.8 | 6.35 | -0.65 | 1.1765 | 4.885e-15 | Sprint End
Total: | 28 |  |  | 20.65
Sprint 8 - Orion
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-22 | 0 | N/A | N/A | N/A | #N/A | 22 | 22 | 22 | Sprint start
2022-02-23 | 2 | User Analysis Dashboard | 70% | 1.4 | 13.6 | 20.6 | 1.8333 | 20.1667
2022-02-24 | 2 | User Analysis Dashboard | 80% | 1.6 | 12 | 19 | 1.8333 | 18.3333
2022-02-25 | 0 | N/A | 0% | 0 | #N/A | 19 | 1.8333 | 16.5
2022-02-26 | 3 | User Analysis Dashboard | 80% | 2.4 | 9.6 | 16.6 | 1.8333 | 14.6667
2022-02-27 | 2 | User Analysis Dashboard | 90% | 1.8 | 7.8 | 14.8 | 1.8333 | 12.8333
2022-02-28 | 3 | User Analysis Dashboard | 75% | 2.25 | 5.55 | 12.55 | 1.8333 | 11
2022-03-01 | 0 | N/A | 0% | 0 | #N/A | 12.55 | 1.8333 | 9.1667
2022-03-02 | 3 | User Analysis Dashboard | 60% | 1.8 | 3.75 | 10.75 | 1.8333 | 7.3333
2022-03-03 | 0 | N/A | 0% | 0 | #N/A | 10.75 | 1.8333 | 5.5
2022-03-04 | 4 | User Analysis Dashboard | 80% | 3.2 | 0.55 | 7.55 | 1.8333 | 3.6667
2022-03-05 | 2 | User Analysis Dashboard | 75% | 1.5 | -0.95 | 6.05 | 1.8333 | 1.8333
2022-03-06 | 6 | User Analysis Dashboard | 80% | 4.8 | -5.75 | 1.25 | 1.8333 | 2.2204e-15 | Sprint End
Total: | 27 |  |  | 20.75
Sprint 9 - Orion
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-08 | 0 | N/A | N/A | N/A | #N/A | 11 | 11 | 11 | Sprint start
2022-03-09 | 0 | N/A | 0% | 0 | #N/A | 11 | 1.1 | 9.9
2022-03-10 | 0 | N/A | 0% | 0 | #N/A | 11 | 1.1 | 8.8
2022-03-11 | 3 | Account Creation - Finish | 80% | 2.4 | 6.6 | 8.6 | 1.1 | 7.7
2022-03-12 | 3 | Account Creation - Finish | 75% | 2.25 | 4.35 | 6.35 | 1.1 | 6.6
2022-03-13 | 0 | N/A | 0% | 0 | #N/A | 6.35 | 1.1 | 5.5
2022-03-14 | 4 | Account Creation - Finish | 85% | 3.4 | 0.95 | 2.95 | 1.1 | 4.4
2022-03-15 | 0 | N/A | 80% | 0 | #N/A | 2.95 | 1.1 | 3.3
2022-03-16 | 2 | Account Creation - Finish | 80% | 1.6 | -0.65 | 1.35 | 1.1 | 2.2
2022-03-17 | 0 | N/A | 0% | 0 | #N/A | 1.35 | 1.1 | 1.1
2022-03-18 | 2 | Account Creation - Finish | 80% | 1.6 | -2.25 | -0.25 | 1.1 | 1.7764e-15 | Sprint End
Total: | 14 |  |  | 11.25
Sprint 10 - Orion
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-28 | 0 | N/A | N/A | N/A | #N/A | 18 | 18 | 18 | Sprint start
2022-03-29 | 0 | N/A | 0% | 0 | #N/A | 18 | 0.85714 | 17.1429
2022-03-30 | 2 | Feature - Hazard Labels | 80% | 1.6 | 16.4 | 16.4 | 0.85714 | 16.2857
2022-03-31 | 2 | N/A | 0% | 0 | #N/A | 16.4 | 0.85714 | 15.4286
2022-04-01 | 3 | Feature - Hazard Labels | 75% | 2.25 | 14.15 | 14.15 | 0.85714 | 14.5714
2022-04-02 | 0 | N/A | 0% | 0 | #N/A | 14.15 | 0.85714 | 13.7143
2022-04-03 | 0 | N/A | 0% | 0 | #N/A | 14.15 | 0.85714 | 12.8571
2022-04-04 | 3 | Feature - Hazard Labels | 60% | 1.8 | 12.35 | 12.35 | 0.85714 | 12
2022-04-05 | 2 | Feature - Hazard Labels | 80% | 1.6 | 10.75 | 10.75 | 0.85714 | 11.1429
2022-04-06 | 0 | N/A | 0% | 0 | #N/A | 10.75 | 0.85714 | 10.2857
2022-04-07 | 0 | N/A | 0% | 0 | #N/A | 10.75 | 0.85714 | 9.4286
2022-04-08 | 4 | Feature - Hazard Labels | 80% | 3.2 | 7.55 | 7.55 | 0.85714 | 8.5714
2022-04-09 | 3 | Feature - Hazard Labels | 65% | 1.95 | 5.6 | 5.6 | 0.85714 | 7.7143
2022-04-10 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | 6.8571
2022-04-11 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | 6
2022-04-12 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | 5.1429
2022-04-13 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | 4.2857
2022-04-14 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | 3.4286
2022-04-15 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | 2.5714
2022-04-16 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | 1.7143
2022-04-17 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | 0.85714
2022-04-18 | 0 | N/A | 0% | 0 | #N/A | 5.6 | 0.85714 | -3.7748e-15 | Sprint End
Total: | 19 |  |  | 12.4

## Leon Burndown
Sprint 7 - Leon
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 18 | 18 | 18 | Sprint start
2022-02-04 | 1 | Authentication | 60% | 0.6 | 15.4 | 17.4 | 1.0588 | 16.9412
2022-02-05 | 0 | N/A | 0% | 0 | N/A | 17.4 | 1.0588 | 15.8824
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 17.4 | 1.0588 | 14.8235
2022-02-07 | 2 | Authentication | 75% | 1.5 | 13.9 | 15.9 | 1.0588 | 13.7647
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 15.9 | 1.0588 | 12.7059
2022-02-09 | 3 | Authentication | 0% | 0 | 13.9 | 15.9 | 1.0588 | 11.6471
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 15.9 | 1.0588 | 10.5882
2022-02-11 | 5 | Authentication | 70% | 3.5 | 10.4 | 12.4 | 1.0588 | 9.5294
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 12.4 | 1.0588 | 8.4706
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 12.4 | 1.0588 | 7.4118
2022-02-14 | 3 | Authentication | 60% | 1.8 | 8.6 | 10.6 | 1.0588 | 6.3529
2022-02-15 | 3 | Authentication | 90% | 2.7 | 5.9 | 7.9 | 1.0588 | 5.2941
2022-02-16 | 6 | Authentication | 85% | 5.1 | 0.8 | 2.8 | 1.0588 | 4.2353
2022-02-17 | 0 | N/A | 0% | 0 | N/A | 2.8 | 1.0588 | 3.1765
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 2.8 | 1.0588 | 2.1176
2022-02-19 | 6 | Authentication | 59.5% | 3.57 | -2.77 | -0.77 | 1.0588 | 1.0588
2022-02-20 | 4 | Authentication | 60% | 2.4 | -5.17 | -3.17 | 1.0588 | 3.1086e-15 | Sprint End
Total: | 33 |  |  | 21.17
Sprint 8 - Leon
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-22 | 0 | N/A | N/A | N/A | #N/A | 25 | 25 | 25 | Sprint start
2022-02-23 | 2 | Authorization | 70% | 1.4 | 15.6 | 23.6 | 2.0833 | 22.9167
2022-02-24 | 3 | Authorization | 80% | 2.4 | 13.2 | 21.2 | 2.0833 | 20.8333
2022-02-25 | 3 | Authorization | 75% | 2.25 | 10.95 | 18.95 | 2.0833 | 18.75
2022-02-26 | 0 | N/A | 0% | 0 | #N/A | 18.95 | 2.0833 | 16.6667
2022-02-27 | 0 | N/A | 0% | 0 | #N/A | 18.95 | 2.0833 | 14.5833
2022-02-28 | 3 | Authorization | 75% | 2.25 | 8.7 | 16.7 | 2.0833 | 12.5
2022-03-01 | 2 | Authorization | 70% | 1.4 | 7.3 | 15.3 | 2.0833 | 10.4167
2022-03-02 | 3 | Authorization | 60% | 1.8 | 5.5 | 13.5 | 2.0833 | 8.3333
2022-03-03 | 0 | N/A | 0% | 0 | #N/A | 13.5 | 2.0833 | 6.25
2022-03-04 | 4 | Authorization | 80% | 3.2 | 2.3 | 10.3 | 2.0833 | 4.1667
2022-03-05 | 2 | Authorization | 75% | 1.5 | 0.8 | 8.8 | 2.0833 | 2.0833
2022-03-06 | 6 | Authorization | 80% | 4.8 | -4 | 4 | 2.0833 | 0 | Sprint End
Total: | 28 |  |  | 21
Sprint 9 - Leon
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-08 | 0 | N/A | N/A | N/A | #N/A | 12 | 12 | 12 | Sprint start
2022-03-09 | 2 | Account Deletion - Finish | 60% | 1.2 | 7.8 | 10.8 | 1.2 | 10.8
2022-03-10 | 0 | N/A | 0% | 0 | #N/A | 10.8 | 1.2 | 9.6
2022-03-11 | 3 | Account Deletion - Finish | 80% | 2.4 | 5.4 | 8.4 | 1.2 | 8.4
2022-03-12 | 0 | N/A | 0% | 0 | #N/A | 8.4 | 1.2 | 7.2
2022-03-13 | 3 | Account Deletion - Finish | 80% | 2.4 | 3 | 6 | 1.2 | 6
2022-03-14 | 0 | N/A | 0% | 0 | #N/A | 6 | 1.2 | 4.8
2022-03-15 | 3 | Account Deletion - Finish | 75% | 2.25 | 0.75 | 3.75 | 1.2 | 3.6
2022-03-16 | 0 | N/A | 0% | 0 | #N/A | 3.75 | 1.2 | 2.4
2022-03-17 | 0 | N/A | 0% | 0 | #N/A | 3.75 | 1.2 | 1.2
2022-03-18 | 2 | Account Deletion - Finish | 75% | 1.5 | -0.75 | 2.25 | 1.2 | 0 | Sprint End
Total: | 13 |  |  | 9.75
Sprint 10 - Leon
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-28 | 0 | N/A | N/A | N/A | #N/A | 22 | 22 | 22 | Sprint start
2022-03-29 | 2 | Feature - Map Overlays | 70% | 1.4 | 15.6 | 20.6 | 1.0476 | 20.9524
2022-03-30 | 3 | Feature - Map Overlays | 80% | 2.4 | 13.2 | 18.2 | 1.0476 | 19.9048
2022-03-31 | 0 | N/A | 0% | 0 | #N/A | 18.2 | 1.0476 | 18.8571
2022-04-01 | 3 | Feature - Map Overlays | 80% | 2.4 | 10.8 | 15.8 | 1.0476 | 17.8095
2022-04-02 | 1 | Feature - Map Overlays | 90% | 0.9 | 9.9 | 14.9 | 1.0476 | 16.7619
2022-04-03 | 0 | N/A | 0% | 0 | #N/A | 14.9 | 1.0476 | 15.7143
2022-04-04 | 0 | N/A | 0% | 0 | #N/A | 14.9 | 1.0476 | 14.6667
2022-04-05 | 2 | Feature - Map Overlays | 65% | 1.3 | 8.6 | 13.6 | 1.0476 | 13.619
2022-04-06 | 4 | Feature - Map Overlays | 70% | 2.8 | 5.8 | 10.8 | 1.0476 | 12.5714
2022-04-07 | 0 | N/A | 0% | 0 | #N/A | 10.8 | 1.0476 | 11.5238
2022-04-08 | 1 | Feature - Map Overlays | 80% | 0.8 | 5 | 10 | 1.0476 | 10.4762
2022-04-09 | 3 | Feature - Map Overlays | 80% | 2.4 | 2.6 | 7.6 | 1.0476 | 9.4286
2022-04-10 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 8.381
2022-04-11 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 7.3333
2022-04-12 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 6.2857
2022-04-13 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 5.2381
2022-04-14 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 4.1905
2022-04-15 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 3.1429
2022-04-16 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 2.0952
2022-04-17 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 1.0476
2022-04-18 | 0 | N/A | 0% | 0 | #N/A | 7.6 | 1.0476 | 3.1086e-15 | Sprint End
Total: | 19 |  |  | 14.4

## An Burndown
Sprint 7 - An
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 12 | 12 | 12 | Sprint start
2022-02-04 | 0 | N/A | 0% | 0 | N/A | 12 | 0.70588 | 11.2941
2022-02-05 | 1 | Logout | 80% | 0.8 | 11.2 | 11.2 | 0.70588 | 10.5882
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 11.2 | 0.70588 | 9.8824
2022-02-07 | 0 | N/A | 0% | 0 | N/A | 11.2 | 0.70588 | 9.1765
2022-02-08 | 2 | Logout | 50% | 1 | 10.2 | 10.2 | 0.70588 | 8.4706
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 7.7647
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 7.0588
2022-02-11 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 6.3529
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 5.6471
2022-02-13 | 2 | Logout | 74% | 1.48 | 8.72 | 8.72 | 0.70588 | 4.9412
2022-02-14 | 1 | Logout | 60% | 0.6 | 8.12 | 8.12 | 0.70588 | 4.2353
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 8.12 | 0.70588 | 3.5294
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 8.12 | 0.70588 | 2.8235
2022-02-17 | 2 | Logout | 70% | 1.4 | 6.72 | 6.72 | 0.70588 | 2.1176
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 6.72 | 0.70588 | 1.4118
2022-02-19 | 1 | Logout | 70% | 0.7 | 6.02 | 6.02 | 0.70588 | 0.70588
2022-02-20 | 0 | N/A | 0% | 0 | N/A | 6.02 | 0.70588 | 1.9984e-15 | Sprint End
Total: | 9 |  |  | 5.98
Sprint 8 - An
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-22 | 0 | N/A | N/A | N/A | #N/A | 20 | 20 | 20 | Sprint start
2022-02-23 | 1 | Logout | 70% | 0.7 | 13.3 | 19.3 | 1.6667 | 18.3333
2022-02-24 | 0 | N/A | 80% | 0 | #N/A | 19.3 | 1.6667 | 16.6667
2022-02-25 | 3 | Logout | 75% | 2.25 | 11.05 | 17.05 | 1.6667 | 15
2022-02-26 | 0 | N/A | 0% | 0 | #N/A | 17.05 | 1.6667 | 13.3333
2022-02-27 | 4 | Logout | 60% | 0 | 11.05 | 17.05 | 1.6667 | 11.6667
2022-02-28 | 3 | Logout | 75% | 2.25 | 8.8 | 14.8 | 1.6667 | 10
2022-03-01 | 2 | 0 | 70% | 1.4 | #N/A | 13.4 | 1.6667 | 8.3333
2022-03-02 | 3 | Logout | 80% | 2.4 | 6.4 | 11 | 1.6667 | 6.6667
2022-03-03 | 0 | N/A | 0% | 0 | #N/A | 11 | 1.6667 | 5
2022-03-04 | 4 | Logout | 80% | 3.2 | 3.2 | 7.8 | 1.6667 | 3.3333
2022-03-05 | 2 | Logout | 75% | 1.5 | 1.7 | 6.3 | 1.6667 | 1.6667
2022-03-06 | 6 | Logout | 80% | 4.8 | -3.1 | 1.5 | 1.6667 | 0 | Sprint End
Total: | 28 |  |  | 18.5
Sprint 9 - An
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-08 | 0 | N/A | N/A | N/A | #N/A | 10 | 10 | 10 | Sprint start
2022-03-09 | 0 | N/A | 0% | 0 | #N/A | 10 | 1 | 9
2022-03-10 | 0 | N/A | 0% | 0 | #N/A | 10 | 1 | 8
2022-03-11 | 0 | N/A | 0% | 0 | #N/A | 10 | 1 | 7
2022-03-12 | 3 | Logout - Finish | 75% | 2.25 | 5.75 | 7.75 | 1 | 6
2022-03-13 | 4 | Logout - Finish | 80% | 3.2 | 2.55 | 4.55 | 1 | 5
2022-03-14 | 0 | N/A | 0% | 0 | #N/A | 4.55 | 1 | 4
2022-03-15 | 3 | Logout - Finish | 80% | 2.4 | 0.15 | 2.15 | 1 | 3
2022-03-16 | 0 | N/A | 80% | 0 | #N/A | 2.15 | 1 | 2
2022-03-17 | 0 | N/A | 70% | 0 | #N/A | 2.15 | 1 | 1
2022-03-18 | 3 | Logout - Finish | 90% | 2.7 | -2.55 | -0.55 | 1 | 0 | Sprint End
Total: | 13 |  |  | 10.55
Sprint 10 - An
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-03-28 | 0 | N/A | N/A | N/A | #N/A | 15 | 15 | 15 | Sprint start
2022-03-29 | 2 | Feature - Safety Analysis | 70% | 1.4 | 12.6 | 13.6 | 0.71429 | 14.2857
2022-03-30 | 0 | N/A | 0% | 0 | #N/A | 13.6 | 0.71429 | 13.5714
2022-03-31 | 0 | N/A | 0% | 0 | #N/A | 13.6 | 0.71429 | 12.8571
2022-04-01 | 2 | Feature - Safety Analysis | 80% | 1.6 | 11 | 12 | 0.71429 | 12.1429
2022-04-02 | 1 | Feature - Safety Analysis | 90% | 0.9 | 10.1 | 11.1 | 0.71429 | 11.4286
2022-04-03 | 0 | N/A | 0% | 0 | #N/A | 11.1 | 0.71429 | 10.7143
2022-04-04 | 2 | Feature - Safety Analysis | 80% | 1.6 | 8.5 | 9.5 | 0.71429 | 10
2022-04-05 | 0 | N/A | 0% | 0 | #N/A | 9.5 | 0.71429 | 9.2857
2022-04-06 | 0 | N/A | 0% | 0 | #N/A | 9.5 | 0.71429 | 8.5714
2022-04-07 | 1 | Feature - Safety Analysis | 80% | 0.8 | 7.7 | 8.7 | 0.71429 | 7.8571
2022-04-08 | 0 | N/A | 0% | 0 | #N/A | 8.7 | 0.71429 | 7.1429
2022-04-09 | 2 | Feature - Safety Analysis | 60% | 1.2 | 6.5 | 7.5 | 0.71429 | 6.4286
2022-04-10 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 5.7143
2022-04-11 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 5
2022-04-12 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 4.2857
2022-04-13 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 3.5714
2022-04-14 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 2.8571
2022-04-15 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 2.1429
2022-04-16 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 1.4286
2022-04-17 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 0.71429
2022-04-18 | 0 | N/A | 0% | 0 | #N/A | 7.5 | 0.71429 | 5.5511e-15 | Sprint End
Total: | 10 |  |  | 7.5

## Team Burndown
Sprint 8 - Team
Date | Hours Worked | Total Story Points Completed (Actual) | Total Story Points Remaining in Work Items (Actual) | Total Story Points Remaining in Capacity (Actual) | Total Story Points Completed (Ideal) | Total Story Points Remaining (Ideal )
2022-02-22 | 0 | 0 | 102 | 104 | 102 | 102 | Sprint start
2022-02-23 | 3 | 6.3 | 95.7 | 97.7 | 8.5 | 93.5
2022-02-24 | 10 | 8.4 | 87.3 | 89.3 | 8.5 | 85
2022-02-25 | 3 | 4.5 | 82.8 | 84.8 | 8.5 | 76.5
2022-02-26 | 4 | 4.8 | 78 | 80 | 8.5 | 68
2022-02-27 | 4 | 4.2 | 73.8 | 75.8 | 8.5 | 59.5
2022-02-28 | 5 | 12.75 | 61.05 | 63.05 | 8.5 | 51
2022-03-01 | 3 | 4 | 57.05 | 59.05 | 8.5 | 42.5
2022-03-02 | 10 | 10.8 | 46.25 | 48.25 | 8.5 | 34
2022-03-03 | 3 | 4.5 | 41.75 | 43.75 | 8.5 | 25.5
2022-03-04 | 4 | 16 | 25.75 | 27.75 | 8.5 | 17
2022-03-05 | 11 | 11.25 | 14.5 | 16.5 | 8.5 | 8.5
2022-03-06 | 10 | 24.8 | -10.3 | -8.3 | 8.5 | 0 | Sprint End
Total: | 70 | 112.3 | -10.3 | -8.3
Sprint 9 - Team
Date | Hours Worked | Total Story Points Completed (Actual) | Total Story Points Remaining in Work Items (Actual) | Total Story Points Remaining in Capacity (Actual) | Total Story Points Completed (Ideal) | Total Story Points Remaining (Ideal )
2022-03-08 | 0 | 0 | 45 | 41 | 45 | 45 | Sprint start
2022-03-09 | 5 | 3 | 42 | 38 | 4.5 | 40.5
2022-03-10 | 0 | 0 | 42 | 38 | 4.5 | 36
2022-03-11 | 9 | 7.2 | 34.8 | 30.8 | 4.5 | 31.5
2022-03-12 | 12 | 9 | 25.8 | 21.8 | 4.5 | 27
2022-03-13 | 9 | 7.2 | 18.6 | 14.6 | 4.5 | 22.5
2022-03-14 | 4 | 3.4 | 15.2 | 11.2 | 4.5 | 18
2022-03-15 | 9 | 7.05 | 8.15 | 4.15 | 4.5 | 13.5
2022-03-16 | 5 | 3.4 | 4.75 | 0.75 | 4.5 | 9
2022-03-17 | 6 | 2.1 | 2.65 | -1.35 | 4.5 | 4.5
2022-03-18 | 11 | 9 | -6.35 | -10.35 | 4.5 | 0 | Sprint End
Total: | 70 | 51.35 | -6.35 | -10.35
Sprint 10 - Team
Date | Hours Worked | Total Story Points Completed (Actual) | Total Story Points Remaining in Work Items (Actual) | Total Story Points Remaining in Capacity (Actual) | Total Story Points Completed (Ideal) | Total Story Points Remaining (Ideal )
2022-03-28 | 0 | 0 | 89 | 99 | 99 | 99 | Sprint start
2022-03-29 | 6 | 4.2 | 84.8 | 94.8 | 4.7143 | 94.2857
2022-03-30 | 8 | 6.1 | 78.7 | 88.7 | 4.7143 | 89.5714
2022-03-31 | 4 | 1.5 | 77.2 | 87.2 | 4.7143 | 84.8571
2022-04-01 | 12 | 9.45 | 67.75 | 77.75 | 4.7143 | 80.1429
2022-04-02 | 2 | 1.8 | 65.95 | 75.95 | 4.7143 | 75.4286
2022-04-03 | 4 | 3.6 | 62.35 | 72.35 | 4.7143 | 70.7143
2022-04-04 | 9 | 5.8 | 56.55 | 66.55 | 4.7143 | 66
2022-04-05 | 7 | 5.3 | 51.25 | 61.25 | 4.7143 | 61.2857
2022-04-06 | 4 | 2.8 | 48.45 | 58.45 | 4.7143 | 56.5714
2022-04-07 | 3 | 2.3 | 46.15 | 56.15 | 4.7143 | 51.8571
2022-04-08 | 7 | 5.6 | 40.55 | 50.55 | 4.7143 | 47.1429
2022-04-09 | 12 | 8.65 | 31.9 | 41.9 | 4.7143 | 42.4286
2022-04-10 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 37.7143
2022-04-11 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 33
2022-04-12 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 28.2857
2022-04-13 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 23.5714
2022-04-14 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 18.8571
2022-04-15 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 14.1429
2022-04-16 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 9.4286
2022-04-17 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 4.7143
2022-04-18 | 0 | 0 | 31.9 | 41.9 | 4.7143 | 3.0198e-14 | Sprint End
Total: | 78 | 57.1 | 31.9 | 41.9

## Sprint Velocity Analysis
| Sprint | Team Member | Work Item | Estimated Capacity | Velocity (Actual Capacity) | % Error
| 3 | Colin | Test Plan | 28 | 46 | 64.3%
|  | An | Network Diagram | 12 | 10 | -16.7%
|  | Andy | Test Plan | 8 | 9 | 12.5%
|  | Orion | Test Plan | 13 | 15 | 15.4%
|  | Leon | Project Plan | 11 | 9 | -18.2%
|  | Total | All | 72 | 89 | 23.6%
| 4 | Colin | Logging | 15 | 23 | 53.3%
|  | An | React DAR | 6 | 8 | 33.3%
|  | Andy | CSS DAR | 11 | 14 | 27.3%
|  | Orion | Update BRD | 7 | 6 | -14.3%
|  | Leon | Vue DAR | 8 | 10 | 25%
|  | Total | All | 47 | 61 | 29.8%
| 5 | Colin | Logging | 40 | 62 | 55%
|  | An | UM Sequence Diagrams | 14 | 12 | -14.3%
|  | Andy | Logging CRC Cards | 17 | 16 | -5.9%
|  | Orion | Logging LLD | 22 | 25 | 13.6%
|  | Leon | UM LLD | 18 | 16 | -11.1%
|  | Total | All | 111 | 131 | 18%
| 6 | Colin | **N/A** | **N/A** | **N/A** | 53%
|  | An | Security LLD | 6 | 10 | 66.7%
|  | Andy | Test Suite DAR | 7 | 12 | 71.4% | 3
|  | Orion | DB Setup | 11 | 15 | 36.4% | 4
|  | Leon | UM Source Code | 8 | 11 | 37.5% | 5
|  | Total | All | 32 | 48 | 50% | 6
| 7 | Colin | New Feature/Authorization | 18 | 20.7 | 14.7% | 7
|  | An | Logout | 16 | 6 | -62.6% | 8
|  | Andy | Account Creation | 24 | 6 | -75% | 9
|  | Orion | Initial App Setup | 20 | 20.7 | 3.3% | 10
|  | Leon | Authentication | 18 | 21.2 | 17.6%
|  | Total | All | 96 | 74.5 | -22.4%
| 8 | Colin | Authentication | 20 | 24.35 | 4.35%
3 |  | An | Logout | 20 | 18.5 | -1.5%
4 |  | Andy | Account Creation, Account Deletion | 18 | 27.7 | 9.7%
5 |  | Orion | User Analysis Dashboard, Account Deletion | 22 | 20.75 | -1.25%
6 |  | Leon | Authentication | 25 | 21 | -4%
7 |  | Total | All | 105 | 112.3 | 7.3%
8 | 9 | Colin | Authentication - Finish | 10 | 11.95 | 1.95%
9 |  | An | Logout - Finish | 10 | 10.55 | 0.55%
10 |  | Andy | Account Creation - Finish | 9 | 7.85 | -1.15%
11 |  | Orion | Account Deletion - Finish | 11 | 11.25 | 0.25%
|  | Leon | Authorization - Finish | 12 | 9.75 | -2.25%
|  | Total | All | 52 | 51.35 | -0.65%
| 10 | Colin | Feature - Hazard Restrictions | 24 | 11.4 | -12.6%
|  | An | Feature - Safety Analysis | 15 | 7.5 | -7.5%
|  | Andy | Feature - Map Directions | 20 | 11.4 | -8.6%
|  | Orion | Feature - Hazard Labels | 18 | 12.4 | -5.6%
|  | Leon | Feature - Map Overlays | 22 | 14.4 | -7.6%
|  | Total | All | 99 | 57.1 | -41.9%
Note on G21: Colin Creasman: **Colin was not a member of this group during Sprint 6 and his old group only did 5 sprints so he has no viable data for Sprint 6. To account for this missing data, we used the average of the other group members' values for Sprint 6**

## Work Items
Sprint | Work Item | Initial Story Point Estimate | Updated Story Point Estimate | Assigned to
7 | Authorization | 8 | 19 | Colin
| Authentication | 10 | 16 | Leon
| Account Creation | 14 | 25 | Andy
| Initial App Setup | 8 | 27 | Orion
| New Feature | 5 | 7 | Colin
| Logout | 5 | 12 | An
| Total | 50 | 106
8 | Authorization | 16 | 17 | Colin
| Authentication | 16 | 20 | Leon
| Account Creation | 14 | 20 | Andy
| Account Deletion | 14 | 16 | Orion, Andy
| User Analysis Dashboard | 15 | 15 | Colin
| Logout | 12 | 14 | An
| Total | 87 | 102
9 | Authorization - Finish | 8 | 8 | Colin
| Authentication - Finish | 10 | 11 | Leon
| Account Creation - Finish | 8 | 9 | Andy
| Account Deletion - Finish | 7 | 9 | Orion
| Logout - Finish | 7 | 8 | An
| Total | 40 | 45
10 | Feature - Hazard Restrictions | 20 | 19 | Colin
| Feature - Map Overlays | 18 | 17 | Leon
| Feature - Map Directions | 22 | 21 | Andy
| Feature - Hazard Labels | 18 | 18 | Orion
| Feature - Safety Analysis | 16 | 14 | An
| Total | 94 | 89