## Colin Burndown
Sprint 7 - Colin
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 18 | 18 | 18 | Sprint start
2022-02-04 | 2 | New Feature | 60% | 1.2 | 5.8 | 16.8 | 1.0588 | 16.9412
2022-02-05 | 3 | New Feature | 80% | 2.4 | 3.4 | 14.4 | 1.0588 | 15.8824
2022-02-06 | 0 | N/A | 0 | 0 | N/A | 14.4 | 1.0588 | 14.8235
2022-02-07 | 2 | New Feature | 75% | 1.5 | 1.9 | 12.9 | 1.0588 | 13.7647
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 12.9 | 1.0588 | 12.7059
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 12.9 | 1.0588 | 11.6471
2022-02-10 | 1 | Authorization | 60% | 0.6 | 18.4 | 12.3 | 1.0588 | 10.5882
2022-02-11 | 2 | Authorization | 70% | 1.4 | 17 | 10.9 | 1.0588 | 9.5294
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 10.9 | 1.0588 | 8.4706
2022-02-13 | 2 | Authorization | 50% | 1 | 16 | 9.9 | 1.0588 | 7.4118
2022-02-14 | 4 | Authorization | 60% | 2.4 | 13.6 | 7.5 | 1.0588 | 6.3529
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 7.5 | 1.0588 | 5.2941
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 7.5 | 1.0588 | 4.2353
2022-02-17 | 4 | Authorization | 60% | 2.4 | 11.2 | 5.1 | 1.0588 | 3.1765
2022-02-18 | 3 | Authorization | 80% | 2.4 | 8.8 | 2.7 | 1.0588 | 2.1176
2022-02-19 | 4 | Authorization | 40% | 1.6 | 7.2 | 1.1 | 1.0588 | 1.0588
2022-02-20 | 5 | Authorization | 75% | 3.75 | 3.45 | -2.65 | 1.0588 | 3.1086e-15 | Sprint End
Total: | 32 |  |  | 20.65
Sprint 12 - Colin
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-28 | 0 | N/A | N/A | N/A | #N/A | 20 | 20 | 20 | Sprint start
2022-04-29 | 1 | OTP | 30% | 0.3 | #N/A | 19.7 | 1.6667 | 18.3333
2022-04-30 | 0 | N/A | 0% | 0 | #N/A | 19.7 | 1.6667 | 16.6667
2022-05-01 | 1 | OTP | 20% | 0.2 | #N/A | 19.5 | 1.6667 | 15
2022-05-02 | 0 | N/A | 0% | 0 | #N/A | 19.5 | 1.6667 | 13.3333
2022-05-03 | 4 | OTP | 60% | 2.4 | #N/A | 17.1 | 1.6667 | 11.6667
2022-05-04 | 3 | Login | 50% | 1.5 | #N/A | 15.6 | 1.6667 | 10
2022-05-05 | 2 | Login | 30% | 0.6 | #N/A | 15 | 1.6667 | 8.3333
2022-05-06 | 0 | N/A | 0% | 0 | #N/A | 15 | 1.6667 | 6.6667
2022-05-07 | 0 | N/A | 0% | 0 | #N/A | 15 | 1.6667 | 5
2022-05-08 | 8 | Login | 40% | 3.2 | #N/A | 11.8 | 1.6667 | 3.3333
2022-05-09 | 8 | Login | 70% | 5.6 | #N/A | 6.2 | 1.6667 | 1.6667
2022-05-10 | 8 | Login | 80% | 6.4 | #N/A | -0.2 | 1.6667 | 0 | Sprint End
Total: | 35 |  |  | 20.2

## Andy Burndown
Sprint 7 - Andy
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 24 | 24 | 24 | Sprint start
2022-02-04 | 0 | N/A | 0% | 0 | N/A | 24 | 1.4118 | 22.5882
2022-02-05 | 4 | Account Creation | 25% | 1 | 24 | 23 | 1.4118 | 21.1765
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 19.7647
2022-02-07 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 18.3529
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 16.9412
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 15.5294
2022-02-10 | 2 | Account Creation | 60% | 1.2 | 22.8 | 21.8 | 1.4118 | 14.1176
2022-02-11 | 0 | N/A | 0% | 0 | N/A | 21.8 | 1.4118 | 12.7059
2022-02-12 | 2 | Account Creation | 50% | 1 | 21.8 | 20.8 | 1.4118 | 11.2941
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 9.8824
2022-02-14 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 8.4706
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 7.0588
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 5.6471
2022-02-17 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 4.2353
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 2.8235
2022-02-19 | 4 | Account Creation | 70% | 2.8 | 19 | 18 | 1.4118 | 1.4118
2022-02-20 | 0 | N/A | 0% | 0 | N/A | 18 | 1.4118 | 3.9968e-15 | Sprint End
Total: | 12 |  |  | 6
Sprint 12 - Andy
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-28 | 0 | N/A | N/A | N/A | #N/A | 18 | 18 | 18 | Sprint start
2022-04-29 | 0 | N/A | 0% | 0 | #N/A | 18 | 1.5 | 16.5
2022-04-30 | 0 | N/A | 0% | 0 | #N/A | 18 | 1.5 | 15
2022-05-01 | 0 | N/A | 0% | 0 | #N/A | 18 | 1.5 | 13.5
2022-05-02 | 3 | Save Route | 10% | 0.3 | #N/A | 17.7 | 1.5 | 12
2022-05-03 | 0 | N/A | 0% | 0 | #N/A | 17.7 | 1.5 | 10.5
2022-05-04 | 5 | Save Route | 10% | 0.5 | #N/A | 17.2 | 1.5 | 9
2022-05-05 | 5 | Save Route | 10% | 0.5 | #N/A | 16.7 | 1.5 | 7.5
2022-05-06 | 5 | Save Route | 10% | 0.5 | #N/A | 16.2 | 1.5 | 6
2022-05-07 | 5 | Save Route | 20% | 1 | #N/A | 15.2 | 1.5 | 4.5
2022-05-08 | 10 | Save Route | 20% | 2 | #N/A | 13.2 | 1.5 | 3
2022-05-09 | 10 | Save Route | 20% | 2 | #N/A | 11.2 | 1.5 | 1.5
2022-05-10 | 10 | Save Route | 30% | 3 | #N/A | 8.2 | 1.5 | 0 | Sprint End
Total: | 53 |  |  | 9.8

## Orion Burndown
Sprint 7 - Orion
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 20 | 20 | 20 | Sprint start
2022-02-04 | 0 | N/A | 0 | 0 | N/A | 20 | 1.1765 | 18.8235
2022-02-05 | 2 | Initial App Setup | 75% | 1.5 | 25.5 | 18.5 | 1.1765 | 17.6471
2022-02-06 | 3 | Initial App Setup | 60% | 1.8 | 23.7 | 16.7 | 1.1765 | 16.4706
2022-02-07 | 0 | N/A | 75% | 0 | N/A | 16.7 | 1.1765 | 15.2941
2022-02-08 | 2 | Initial App Setup | 80% | 1.6 | 22.1 | 15.1 | 1.1765 | 14.1176
2022-02-09 | 2 | Initial App Setup | 80% | 1.6 | 20.5 | 13.5 | 1.1765 | 12.9412
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 13.5 | 1.1765 | 11.7647
2022-02-11 | 3 | Initial App Setup | 70% | 2.1 | 18.4 | 11.4 | 1.1765 | 10.5882
2022-02-12 | 1 | Initial App Setup | 90% | 0.9 | 17.5 | 10.5 | 1.1765 | 9.4118
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 10.5 | 1.1765 | 8.2353
2022-02-14 | 3 | Initial App Setup | 60% | 1.8 | 15.7 | 8.7 | 1.1765 | 7.0588
2022-02-15 | 2 | Initial App Setup | 90% | 1.8 | 13.9 | 6.9 | 1.1765 | 5.8824
2022-02-16 | 3 | Initial App Setup | 85% | 2.55 | 11.35 | 4.35 | 1.1765 | 4.7059
2022-02-17 | 2 | Initial App Setup | 60% | 1.2 | 10.15 | 3.15 | 1.1765 | 3.5294
2022-02-18 | 0 | N/A | 0 | 0 | N/A | 3.15 | 1.1765 | 2.3529
2022-02-19 | 4 | Initial App Setup | 75% | 3 | 7.15 | 0.15 | 1.1765 | 1.1765
2022-02-20 | 1 | Initial App Setup | 80% | 0.8 | 6.35 | -0.65 | 1.1765 | 4.885e-15 | Sprint End
Total: | 28 |  |  | 20.65
Sprint 12 - Orion
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-28 | 0 | N/A | N/A | N/A | #N/A | 22 | 22 | 22 | Sprint start
2022-04-29 | 0 | N/A | 0% | 0 | #N/A | 22 | 1.8333 | 20.1667
2022-04-30 | 4 | User Management | 40% | 1.6 | #N/A | 20.4 | 1.8333 | 18.3333
2022-05-01 | 5 | User Management | 20% | 1 | #N/A | 19.4 | 1.8333 | 16.5
2022-05-02 | 0 | N/A | 0% | 0 | #N/A | 19.4 | 1.8333 | 14.6667
2022-05-03 | 0 | N/A | 0% | 0 | #N/A | 19.4 | 1.8333 | 12.8333
2022-05-04 | 3 | User Management | 60% | 1.8 | #N/A | 17.6 | 1.8333 | 11
2022-05-05 | 6 | User Management | 60% | 3.6 | #N/A | 14 | 1.8333 | 9.1667
2022-05-06 | 0 | N/A | 0% | 0 | #N/A | 14 | 1.8333 | 7.3333
2022-05-07 | 0 | N/A | 0% | 0 | #N/A | 14 | 1.8333 | 5.5
2022-05-08 | 4 | User Management | 80% | 3.2 | #N/A | 10.8 | 1.8333 | 3.6667
2022-05-09 | 5 | User Management | 75% | 3.75 | #N/A | 7.05 | 1.8333 | 1.8333
2022-05-10 | 6 | User Management | 80% | 4.8 | #N/A | 2.25 | 1.8333 | 2.2204e-15 | Sprint End
Total: | 33 |  |  | 19.75

## Leon Burndown
Sprint 7 - Leon
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 18 | 18 | 18 | Sprint start
2022-02-04 | 1 | Authentication | 60% | 0.6 | 15.4 | 17.4 | 1.0588 | 16.9412
2022-02-05 | 0 | N/A | 0% | 0 | N/A | 17.4 | 1.0588 | 15.8824
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 17.4 | 1.0588 | 14.8235
2022-02-07 | 2 | Authentication | 75% | 1.5 | 13.9 | 15.9 | 1.0588 | 13.7647
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 15.9 | 1.0588 | 12.7059
2022-02-09 | 3 | Authentication | 0% | 0 | 13.9 | 15.9 | 1.0588 | 11.6471
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 15.9 | 1.0588 | 10.5882
2022-02-11 | 5 | Authentication | 70% | 3.5 | 10.4 | 12.4 | 1.0588 | 9.5294
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 12.4 | 1.0588 | 8.4706
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 12.4 | 1.0588 | 7.4118
2022-02-14 | 3 | Authentication | 60% | 1.8 | 8.6 | 10.6 | 1.0588 | 6.3529
2022-02-15 | 3 | Authentication | 90% | 2.7 | 5.9 | 7.9 | 1.0588 | 5.2941
2022-02-16 | 6 | Authentication | 85% | 5.1 | 0.8 | 2.8 | 1.0588 | 4.2353
2022-02-17 | 0 | N/A | 0% | 0 | N/A | 2.8 | 1.0588 | 3.1765
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 2.8 | 1.0588 | 2.1176
2022-02-19 | 6 | Authentication | 59.5% | 3.57 | -2.77 | -0.77 | 1.0588 | 1.0588
2022-02-20 | 4 | Authentication | 60% | 2.4 | -5.17 | -3.17 | 1.0588 | 3.1086e-15 | Sprint End
Total: | 33 |  |  | 21.17
Sprint 12 - Leon
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-28 | 0 | N/A | N/A | N/A | #N/A | 25 | 25 | 25 | Sprint start
2022-04-29 | 4 | Share Route | 80% | 3.2 | #N/A | 21.8 | 2.0833 | 22.9167
2022-04-30 | 3 | Share Route | 80% | 2.4 | #N/A | 19.4 | 2.0833 | 20.8333
2022-05-01 | 3 | Share Route | 75% | 2.25 | #N/A | 17.15 | 2.0833 | 18.75
2022-05-02 | 4 | Share Route | 80% | 3.2 | #N/A | 13.95 | 2.0833 | 16.6667
2022-05-03 | 5 | Share Route | 90% | 0 | #N/A | 13.95 | 2.0833 | 14.5833
2022-05-04 | 3 | Share Route | 80% | 2.4 | #N/A | 11.55 | 2.0833 | 12.5
2022-05-05 | 2 | Share Route | 80% | 1.6 | #N/A | 9.95 | 2.0833 | 10.4167
2022-05-06 | 3 | Share Route | 90% | 2.7 | #N/A | 7.25 | 2.0833 | 8.3333
2022-05-07 | 0 | N/A | 0% | 0 | #N/A | 7.25 | 2.0833 | 6.25
2022-05-08 | 0 | N/A | 0% | 0 | #N/A | 7.25 | 2.0833 | 4.1667
2022-05-09 | 0 | N/A | 0% | 0 | #N/A | 7.25 | 2.0833 | 2.0833
2022-05-10 | 0 | N/A | 0% | 0 | #N/A | 7.25 | 2.0833 | 0 | Sprint End
Total: | 27 |  |  | 17.75

## An Burndown
Sprint 7 - An
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 12 | 12 | 12 | Sprint start
2022-02-04 | 0 | N/A | 0% | 0 | N/A | 12 | 0.70588 | 11.2941
2022-02-05 | 1 | Logout | 80% | 0.8 | 11.2 | 11.2 | 0.70588 | 10.5882
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 11.2 | 0.70588 | 9.8824
2022-02-07 | 0 | N/A | 0% | 0 | N/A | 11.2 | 0.70588 | 9.1765
2022-02-08 | 2 | Logout | 50% | 1 | 10.2 | 10.2 | 0.70588 | 8.4706
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 7.7647
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 7.0588
2022-02-11 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 6.3529
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 5.6471
2022-02-13 | 2 | Logout | 74% | 1.48 | 8.72 | 8.72 | 0.70588 | 4.9412
2022-02-14 | 1 | Logout | 60% | 0.6 | 8.12 | 8.12 | 0.70588 | 4.2353
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 8.12 | 0.70588 | 3.5294
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 8.12 | 0.70588 | 2.8235
2022-02-17 | 2 | Logout | 70% | 1.4 | 6.72 | 6.72 | 0.70588 | 2.1176
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 6.72 | 0.70588 | 1.4118
2022-02-19 | 1 | Logout | 70% | 0.7 | 6.02 | 6.02 | 0.70588 | 0.70588
2022-02-20 | 0 | N/A | 0% | 0 | N/A | 6.02 | 0.70588 | 1.9984e-15 | Sprint End
Total: | 9 |  |  | 5.98
Sprint 8 - An
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-04-28 | 0 | N/A | N/A | N/A | #N/A | 20 | 20 | 20 | Sprint start
2022-04-29 | 0 | N/A | 0% | 0 | #N/A | 20 | 1.6667 | 18.3333
2022-04-30 | 0 | N/A | 0% | 0 | #N/A | 20 | 1.6667 | 16.6667
2022-05-01 | 3 | Account Creation | 75% | 2.25 | 17.75 | 17.75 | 1.6667 | 15
2022-05-02 | 2 | Account Creation | 50% | 1 | 16.75 | 16.75 | 1.6667 | 13.3333
2022-05-03 | 3 | Account Creation | 50% | 0 | 16.75 | 16.75 | 1.6667 | 11.6667
2022-05-04 | 0 | N/A | 0% | 0 | #N/A | 16.75 | 1.6667 | 10
2022-05-05 | 0 | N/A | 0% | 0 | #N/A | 16.75 | 1.6667 | 8.3333
2022-05-06 | 0 | N/A | 0% | 0 | #N/A | 16.75 | 1.6667 | 6.6667
2022-05-07 | 5 | Account Creation | 40% | 2 | 14.75 | 14.75 | 1.6667 | 5
2022-05-08 | 5 | Account Creation | 50% | 2.5 | 12.25 | 12.25 | 1.6667 | 3.3333
2022-05-09 | 6 | Account Creation | 60% | 3.6 | 8.65 | 8.65 | 1.6667 | 1.6667
2022-05-10 | 6 | Account Creation | 60% | 3.6 | 5.05 | 5.05 | 1.6667 | 0 | Sprint End
Total: | 30 |  |  | 14.95

## Team Burndown
Sprint 12 - Team
Date | Hours Worked | Total Story Points Completed (Actual) | Total Story Points Remaining in Work Items (Actual) | Total Story Points Remaining in Capacity (Actual) | Total Story Points Completed (Ideal) | Total Story Points Remaining (Ideal )
2022-04-28 | 0 | 0 | 102 | 104 | 102 | 102 | Sprint start
2022-04-29 | 3 | 3.5 | 98.5 | 100.5 | 8.5 | 93.5
2022-04-30 | 10 | 4 | 94.5 | 96.5 | 8.5 | 85
2022-05-01 | 3 | 5.7 | 88.8 | 90.8 | 8.5 | 76.5
2022-05-02 | 4 | 4.5 | 84.3 | 86.3 | 8.5 | 68
2022-05-03 | 4 | 2.4 | 81.9 | 83.9 | 8.5 | 59.5
2022-05-04 | 5 | 6.2 | 75.7 | 77.7 | 8.5 | 51
2022-05-05 | 3 | 6.3 | 69.4 | 71.4 | 8.5 | 42.5
2022-05-06 | 10 | 3.2 | 66.2 | 68.2 | 8.5 | 34
2022-05-07 | 3 | 3 | 63.2 | 65.2 | 8.5 | 25.5
2022-05-08 | 4 | 10.9 | 52.3 | 54.3 | 8.5 | 17
2022-05-09 | 11 | 14.95 | 37.35 | 39.35 | 8.5 | 8.5
2022-05-10 | 10 | 17.8 | 19.55 | 21.55 | 8.5 | 0 | Sprint End
Total: | 70 | 82.45 | 19.55 | 21.55

## Work Items
Sprint | Work Item | Initial Story Point Estimate | Updated Story Point Estimate | Assigned to
7 | Authorization | 8 | 19 | Colin
| Authentication | 10 | 16 | Leon
| Account Creation | 14 | 25 | Andy
| Initial App Setup | 8 | 27 | Orion
| New Feature | 5 | 7 | Colin
| Logout | 5 | 12 | An
| Total | 50 | 106
7 | Authorization | 16 | 17 | Colin
| Authentication | 16 | 20 | Leon
| Account Creation | 14 | 20 | Andy
| Account Deletion | 14 | 16 | Orion, Andy
| User Analysis Dashboard | 15 | 15 | Colin
| Logout | 12 | 14 | An
| Total | 87 | 102

## Sprint Velocity Analysis
| Sprint | Team Member | Work Item | Estimated Capacity | Velocity (Actual Capacity) | % Error
| 3 | Colin | Test Plan | 28 | 46 | 64.3%
|  | An | Network Diagram | 12 | 10 | -16.7%
|  | Andy | Test Plan | 8 | 9 | 12.5%
|  | Orion | Test Plan | 13 | 15 | 15.4%
|  | Leon | Project Plan | 11 | 9 | -18.2%
|  | Total | All | 72 | 89 | 23.6%
| 4 | Colin | Logging | 15 | 23 | 53.3%
|  | An | React DAR | 6 | 8 | 33.3%
|  | Andy | CSS DAR | 11 | 14 | 27.3%
|  | Orion | Update BRD | 7 | 6 | -14.3%
|  | Leon | Vue DAR | 8 | 10 | 25%
|  | Total | All | 47 | 61 | 29.8%
| 5 | Colin | Logging | 40 | 62 | 55%
|  | An | UM Sequence Diagrams | 14 | 12 | -14.3%
|  | Andy | Logging CRC Cards | 17 | 16 | -5.9%
|  | Orion | Logging LLD | 22 | 25 | 13.6%
|  | Leon | UM LLD | 18 | 16 | -11.1%
|  | Total | All | 111 | 131 | 18%
| 6 | Colin | **N/A** | **N/A** | **N/A** | 53%
|  | An | Security LLD | 6 | 10 | 66.7%
|  | Andy | Test Suite DAR | 7 | 12 | 71.4%
|  | Orion | DB Setup | 11 | 15 | 36.4%
|  | Leon | UM Source Code | 8 | 11 | 37.5%
|  | Total | All | 32 | 48 | 50%
| 7 | Colin | New Feature/Authorization | 18 | 20.7 | 14.7%
|  | An | Logout | 16 | 6 | -62.6%
|  | Andy | Account Creation | 24 | 6 | -75%
|  | Orion | Initial App Setup | 20 | 20.7 | 3.3%
|  | Leon | Authentication | 18 | 21.2 | 17.6%
|  | Total | All | 96 | 74.5 | -22.4%
| 8 | Colin | Authentication | 20 | 20.2 | 0.2%
3 |  | An | Logout | 20 | 14.95 | -5.05%
4 |  | Andy | Account Creation, Account Deletion | 18 | 9.8 | -8.2%
5 |  | Orion | User Analysis Dashboard, Account Deletion | 22 | 19.75 | -2.25%
6 |  | Leon | Authentication | 25 | 17.75 | -7.25%
7 |  | Total | All | 105 | 82.45 | -22.55%
8
9
10
11
Note on G21: Colin Creasman: **Colin was not a member of this group during Sprint 6 and his old group only did 5 sprints so he has no viable data for Sprint 6. To account for this missing data, we used the average of the other group members' values for Sprint 6**