## Colin Burndown
Sprint 7 - Colin
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 18 | 18 | 18 | Sprint start
2022-02-04 | 2 | New Feature | 60% | 1.2 | 5.8 | 16.8 | 1.0588 | 16.9412
2022-02-05 | 3 | New Feature | 80% | 2.4 | 3.4 | 14.4 | 1.0588 | 15.8824
2022-02-06 | 0 | N/A | 0 | 0 | N/A | 14.4 | 1.0588 | 14.8235
2022-02-07 | 2 | New Feature | 75% | 1.5 | 1.9 | 12.9 | 1.0588 | 13.7647
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 12.9 | 1.0588 | 12.7059
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 12.9 | 1.0588 | 11.6471
2022-02-10 | 1 | Authorization | 60% | 0.6 | 18.4 | 12.3 | 1.0588 | 10.5882
2022-02-11 | 2 | Authorization | 70% | 1.4 | 17 | 10.9 | 1.0588 | 9.5294
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 10.9 | 1.0588 | 8.4706
2022-02-13 | 2 | Authorization | 50% | 1 | 16 | 9.9 | 1.0588 | 7.4118
2022-02-14 | 4 | Authorization | 60% | 2.4 | 13.6 | 7.5 | 1.0588 | 6.3529
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 7.5 | 1.0588 | 5.2941
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 7.5 | 1.0588 | 4.2353
2022-02-17 | 4 | Authorization | 60% | 2.4 | 11.2 | 5.1 | 1.0588 | 3.1765
2022-02-18 | 3 | Authorization | 80% | 2.4 | 8.8 | 2.7 | 1.0588 | 2.1176
2022-02-19 | 4 | Authorization | 40% | 1.6 | 7.2 | 1.1 | 1.0588 | 1.0588
2022-02-20 | 5 | Authorization | 75% | 3.75 | 3.45 | -2.65 | 1.0588 | 3.1086e-15 | Sprint End
Total: | 32 |  |  | 20.65

## Andy Burndown
Sprint 7 - Andy
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 24 | 24 | 24 | Sprint start
2022-02-04 | 0 | N/A | 0% | 0 | N/A | 24 | 1.4118 | 22.5882
2022-02-05 | 4 | Account Creation | 25% | 1 | 24 | 23 | 1.4118 | 21.1765
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 19.7647
2022-02-07 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 18.3529
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 16.9412
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 23 | 1.4118 | 15.5294
2022-02-10 | 2 | Account Creation | 60% | 1.2 | 22.8 | 21.8 | 1.4118 | 14.1176
2022-02-11 | 0 | N/A | 0% | 0 | N/A | 21.8 | 1.4118 | 12.7059
2022-02-12 | 2 | Account Creation | 50% | 1 | 21.8 | 20.8 | 1.4118 | 11.2941
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 9.8824
2022-02-14 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 8.4706
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 7.0588
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 5.6471
2022-02-17 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 4.2353
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 20.8 | 1.4118 | 2.8235
2022-02-19 | 4 | Account Creation | 70% | 2.8 | 19 | 18 | 1.4118 | 1.4118
2022-02-20 | 0 | N/A | 0% | 0 | N/A | 18 | 1.4118 | 3.9968e-15 | Sprint End
Total: | 12 |  |  | 6

## Orion Burndown
Sprint 7 - Orion
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 20 | 20 | 20 | Sprint start
2022-02-04 | 0 | N/A | 0 | 0 | N/A | 20 | 1.1765 | 18.8235
2022-02-05 | 2 | Initial App Setup | 75% | 1.5 | 25.5 | 18.5 | 1.1765 | 17.6471
2022-02-06 | 3 | Initial App Setup | 60% | 1.8 | 23.7 | 16.7 | 1.1765 | 16.4706
2022-02-07 | 0 | N/A | 75% | 0 | N/A | 16.7 | 1.1765 | 15.2941
2022-02-08 | 2 | Initial App Setup | 80% | 1.6 | 22.1 | 15.1 | 1.1765 | 14.1176
2022-02-09 | 2 | Initial App Setup | 80% | 1.6 | 20.5 | 13.5 | 1.1765 | 12.9412
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 13.5 | 1.1765 | 11.7647
2022-02-11 | 3 | Initial App Setup | 70% | 2.1 | 18.4 | 11.4 | 1.1765 | 10.5882
2022-02-12 | 1 | Initial App Setup | 90% | 0.9 | 17.5 | 10.5 | 1.1765 | 9.4118
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 10.5 | 1.1765 | 8.2353
2022-02-14 | 3 | Initial App Setup | 60% | 1.8 | 15.7 | 8.7 | 1.1765 | 7.0588
2022-02-15 | 2 | Initial App Setup | 90% | 1.8 | 13.9 | 6.9 | 1.1765 | 5.8824
2022-02-16 | 3 | Initial App Setup | 85% | 2.55 | 11.35 | 4.35 | 1.1765 | 4.7059
2022-02-17 | 2 | Initial App Setup | 60% | 1.2 | 10.15 | 3.15 | 1.1765 | 3.5294
2022-02-18 | 0 | N/A | 0 | 0 | N/A | 3.15 | 1.1765 | 2.3529
2022-02-19 | 4 | Initial App Setup | 75% | 3 | 7.15 | 0.15 | 1.1765 | 1.1765
2022-02-20 | 1 | Initial App Setup | 80% | 0.8 | 6.35 | -0.65 | 1.1765 | 4.885e-15 | Sprint End
Total: | 28 |  |  | 20.65

## Leon Burndown
Sprint 7 - Leon
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 18 | 18 | 18 | Sprint start
2022-02-04 | 1 | Authentication | 60% | 0.6 | 15.4 | 17.4 | 1.0588 | 16.9412
2022-02-05 | 0 | N/A | 0% | 0 | N/A | 17.4 | 1.0588 | 15.8824
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 17.4 | 1.0588 | 14.8235
2022-02-07 | 2 | Authentication | 75% | 1.5 | 13.9 | 15.9 | 1.0588 | 13.7647
2022-02-08 | 0 | N/A | 0% | 0 | N/A | 15.9 | 1.0588 | 12.7059
2022-02-09 | 3 | Authentication | 0% | 0 | 13.9 | 15.9 | 1.0588 | 11.6471
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 15.9 | 1.0588 | 10.5882
2022-02-11 | 5 | Authentication | 70% | 3.5 | 10.4 | 12.4 | 1.0588 | 9.5294
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 12.4 | 1.0588 | 8.4706
2022-02-13 | 0 | N/A | 0% | 0 | N/A | 12.4 | 1.0588 | 7.4118
2022-02-14 | 3 | Authentication | 60% | 1.8 | 8.6 | 10.6 | 1.0588 | 6.3529
2022-02-15 | 3 | Authentication | 90% | 2.7 | 5.9 | 7.9 | 1.0588 | 5.2941
2022-02-16 | 6 | Authentication | 85% | 5.1 | 0.8 | 2.8 | 1.0588 | 4.2353
2022-02-17 | 0 | N/A | 0% | 0 | N/A | 2.8 | 1.0588 | 3.1765
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 2.8 | 1.0588 | 2.1176
2022-02-19 | 6 | Authentication | 59.5% | 3.57 | -2.77 | -0.77 | 1.0588 | 1.0588
2022-02-20 | 4 | Authentication | 60% | 2.4 | -5.17 | -3.17 | 1.0588 | 3.1086e-15 | Sprint End
Total: | 33 |  |  | 21.17

## An Burndown
Sprint 7 - An
Date | Hours Worked | Work Item | Productivity | Actual Story Points Completed | Story Points Remaining in Work Item | Story Points Remaining in Capacity | Ideal Story Points Completed | Ideal Story Points Remaining
2022-02-03 | 0 | N/A | N/A | N/A | N/A | 12 | 12 | 12 | Sprint start
2022-02-04 | 0 | N/A | 0% | 0 | N/A | 12 | 0.70588 | 11.2941
2022-02-05 | 1 | Logout | 80% | 0.8 | 11.2 | 11.2 | 0.70588 | 10.5882
2022-02-06 | 0 | N/A | 0% | 0 | N/A | 11.2 | 0.70588 | 9.8824
2022-02-07 | 0 | N/A | 0% | 0 | N/A | 11.2 | 0.70588 | 9.1765
2022-02-08 | 2 | Logout | 50% | 1 | 10.2 | 10.2 | 0.70588 | 8.4706
2022-02-09 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 7.7647
2022-02-10 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 7.0588
2022-02-11 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 6.3529
2022-02-12 | 0 | N/A | 0% | 0 | N/A | 10.2 | 0.70588 | 5.6471
2022-02-13 | 2 | Logout | 74% | 1.48 | 8.72 | 8.72 | 0.70588 | 4.9412
2022-02-14 | 1 | Logout | 60% | 0.6 | 8.12 | 8.12 | 0.70588 | 4.2353
2022-02-15 | 0 | N/A | 0% | 0 | N/A | 8.12 | 0.70588 | 3.5294
2022-02-16 | 0 | N/A | 0% | 0 | N/A | 8.12 | 0.70588 | 2.8235
2022-02-17 | 2 | Logout | 70% | 1.4 | 6.72 | 6.72 | 0.70588 | 2.1176
2022-02-18 | 0 | N/A | 0% | 0 | N/A | 6.72 | 0.70588 | 1.4118
2022-02-19 | 1 | Logout | 70% | 0.7 | 6.02 | 6.02 | 0.70588 | 0.70588
2022-02-20 | 0 | N/A | 0% | 0 | N/A | 6.02 | 0.70588 | 1.9984e-15 | Sprint End
Total: | 9 |  |  | 5.98

## Team Burndown
Sprint 7 - Team
Date | Hours Worked | Total Story Points Completed (Actual) | Total Story Points Remaining in Work Items (Actual) | Total Story Points Remaining in Capacity (Actual) | Total Story Points Completed (Ideal) | Total Story Points Remaining (Ideal )
2022-02-03 | 0 | 0 | 106 | 94 | 94 | 94 | Sprint start
2022-02-04 | 3 | 1.8 | 104.2 | 92.2 | 5.5294 | 88.4706
2022-02-05 | 10 | 5.9 | 98.3 | 86.3 | 5.5294 | 82.9412
2022-02-06 | 3 | 1.8 | 96.5 | 84.5 | 5.5294 | 77.4118
2022-02-07 | 4 | 3 | 93.5 | 81.5 | 5.5294 | 71.8824
2022-02-08 | 4 | 1.6 | 91.9 | 79.9 | 5.5294 | 66.3529
2022-02-09 | 5 | 1.6 | 90.3 | 78.3 | 5.5294 | 60.8235
2022-02-10 | 3 | 3.28 | 87.02 | 75.02 | 5.5294 | 55.2941
2022-02-11 | 10 | 7.6 | 79.42 | 67.42 | 5.5294 | 49.7647
2022-02-12 | 3 | 1.9 | 77.52 | 65.52 | 5.5294 | 44.2353
2022-02-13 | 4 | 1 | 76.52 | 64.52 | 5.5294 | 38.7059
2022-02-14 | 11 | 7.4 | 69.12 | 57.12 | 5.5294 | 33.1765
2022-02-15 | 5 | 4.5 | 64.62 | 52.62 | 5.5294 | 27.6471
2022-02-16 | 9 | 8.35 | 56.27 | 44.27 | 5.5294 | 22.1176
2022-02-17 | 8 | 3.6 | 52.67 | 40.67 | 5.5294 | 16.5882
2022-02-18 | 3 | 2.4 | 50.27 | 38.27 | 5.5294 | 11.0588
2022-02-19 | 19 | 16.95 | 33.32 | 21.32 | 5.5294 | 5.5294
2022-02-20 | 10 | 6.95 | 26.37 | 14.37 | 5.5294 | -2.3093e-14 | Sprint End
Total: | 114 | 79.63 | 26.37 | 14.37

## Work Items
Sprint | Work Item | Initial Story Point Estimate | Updated Story Point Estimate | Assigned to
7 | Authorization | 8 | 19 | Colin
| Authentication | 10 | 16 | Leon
| Account Creation | 14 | 25 | Andy
| Initial App Setup | 8 | 27 | Orion
| New Feature | 5 | 7 | Colin
| Logout | 5 | 12 | An
| Total | 50 | 106

## Sprint Velocity Analysis
| Sprint | Team Member | Work Item | Estimated Capacity | Velocity (Actual Capacity) | % Error
| 3 | Colin | Test Plan | 28 | 46 | 64.3%
|  | An | Network Diagram | 12 | 10 | -16.7%
|  | Andy | Test Plan | 8 | 9 | 12.5%
|  | Orion | Test Plan | 13 | 15 | 15.4%
|  | Leon | Project Plan | 11 | 9 | -18.2%
|  | Total | All | 72 | 89 | 23.6%
| 4 | Colin | Logging | 15 | 23 | 53.3%
|  | An | React DAR | 6 | 8 | 33.3%
|  | Andy | CSS DAR | 11 | 14 | 27.3%
|  | Orion | Update BRD | 7 | 6 | -14.3%
|  | Leon | Vue DAR | 8 | 10 | 25%
|  | Total | All | 47 | 61 | 29.8%
| 5 | Colin | Logging | 40 | 62 | 55%
|  | An | UM Sequence Diagrams | 14 | 12 | -14.3%
|  | Andy | Logging CRC Cards | 17 | 16 | -5.9%
|  | Orion | Logging LLD | 22 | 25 | 13.6%
|  | Leon | UM LLD | 18 | 16 | -11.1%
|  | Total | All | 111 | 131 | 18%
| 6 | Colin | **N/A** | **N/A** | **N/A** | 53%
|  | An | Security LLD | 6 | 10 | 66.7%
|  | Andy | Test Suite DAR | 7 | 12 | 71.4%
|  | Orion | DB Setup | 11 | 15 | 36.4%
|  | Leon | UM Source Code | 8 | 11 | 37.5%
|  | Total | All | 32 | 48 | 50%
| 7 | Colin | New Feature/Authorization | 18 | 20.7 | 14.7%
|  | An | Logout | 16 | 6 | -62.6%
|  | Andy | Account Creation | 24 | 6 | -75%
|  | Orion | Initial App Setup | 20 | 20.7 | 3.3%
|  | Leon | Authentication | 18 | 21.2 | 17.6%
|  | Total | All | 96 | 74.5 | -22.4%
3
4
5
6
7
Note on G21: Colin Creasman: **Colin was not a member of this group during Sprint 6 and his old group only did 5 sprints so he has no viable data for Sprint 6. To account for this missing data, we used the average of the other group members' values for Sprint 6**